## Start Here
START HERE
Read this first · then open Dashboard · upload this file to Google Drive to get a Google Sheet
Hearth & Timber · Home Renovation Management System
A digital twin of the home: every room, material, contractor, expense, document, task, photo, warranty and maintenance activity is connected to a place in the house. This workbook is the complete operating system for a renovation — from first idea through handover and aftercare.
How to use (Excel) |  |  |  |  | How to use (Google Sheets)
1. Enable editing / calculation (Formulas → Automatic). |  |  |  |  | 1. Upload this .xlsx to Google Drive → Open with Google Sheets.
2. Open Settings. Set Active Project ID (PRJ-001 or PRJ-002). |  |  |  |  | 2. File → Save as Google Sheets (keeps formulas, colors, charts).
3. Work in the yellow-ivory input cells. Grey-sand cells are formulas — don't type over them. |  |  |  |  | 3. Extensions → Apps Script → paste google_apps_script/Code.gs.
4. Add rows above the last data row; copy the formula cells down. |  |  |  |  | 4. Reload the sheet. A “Hearth & Timber” menu appears.
5. Use column filters on every register. Status columns are color-coded. |  |  |  |  | 5. Use the menu to add expenses/tasks and send maintenance reminders.
6. Dashboard, Finance and Admin recalculate from the registers. |  |  |  |  | 6. Share with contractors as Commenter or custom-filtered views.
7. File → Print uses tabloid landscape and branded headers. |  |  |  |  | 7. Optional: File → Download to keep an Excel archive.
Color system
Primary #16352F Forest |  | Secondary #E8DDCB Sand |  | Accent #C86B4A Terracotta |  | Background #F8F6F1 Ivory
Success #719B7A Sage |  | Warning #D99A3D Amber |  | Danger #C75C5C Muted red |  | Formula cells (do not type)
Module index (click to jump)
Sheet | What it holds |  |  |  | Sheet | What it holds
Dashboard | Homeowner overview, KPIs, alerts, next tasks |  |  |  | Messages | Threaded communication log
Projects | Multi-project register with live spend |  |  |  | Inventory | Home contents for insurance
Rooms | Spaces, measurements, budgets, photos |  |  |  | Maintenance | Aftercare hub + reminders
Design Studio | Mood boards, palettes, 2D/3D, AI concepts |  |  |  | Inspections | City and independent
AI Insights | Assistant recommendations and savings |  |  |  | Payments | Draws and aging
Budget | Category + room plan vs actual |  |  |  | Change Orders | Scope / cost / schedule deltas
Expenses | Transaction log (Planned / Committed / Paid) |  |  |  | Permits | Authorities and expirations
Finance | Charts, monthly cash, smart alerts |  |  |  | Warranties | Labor and product coverage
Contractors | Profiles + Quality / On-time / Budget / Comms score |  |  |  | Calendar | Visits and deadlines
Quotes | Bid comparison and award |  |  |  | Notifications | Alert queue
Jobs | Assignments, milestones, balances |  |  |  | Users | Nine roles
Tasks | Kanban fields + health + dependencies |  |  |  | Properties | Multi-home digital twin
Timeline | Phase Gantt (weekly) |  |  |  | Admin | Portfolio analytics
Materials | Procurement pipeline + QR / SKU |  |  |  | Settings | Currency, thresholds, brand
Shopping List | Auto list of items still to buy |  |  |  | Lookups | Dropdown lists
Suppliers | Lead times and terms |  |  |  | Audit Log | Who changed what
Documents | Project vault + expiry alerts |  |  |  | Roles & Permissions | Matrix of who can do what
Sample story already loaded
Alex Rivera is renovating 1847 Maplewood Drive, Portland (PRJ-001, $85,000, 72% complete, Construction phase). Kitchen boxes are going in this week; primary bath is on punch list after an AI-led swap from marble to porcelain (about 18% saved on that category). Contingency has dipped under 10%, so the exterior water feature is on hold. A second property — the Columbia Gorge cabin bath (PRJ-002) — is in design so you can see multi-property. Today in the file is 24 August 2026. Change Settings → Today if you reopen this later.
Roles in this system
Homeowner | Admin | Project Manager | Interior Designer | Contractor | Subcontractor | Supplier | Inspector | Accountant

## Dashboard
DASHBOARD
Homeowner overview · live formulas · switch Active Project on Settings
PROGRESS |  |  |  | PHASE |  | BUDGET |  |  | SPENT
[6 empty] | Planned |  |  | Paid to date
COMMITTED |  |  | REMAINING |  | OPEN TASKS |  |  | OVERDUE
Not yet paid |  |  | Still available |  | Not completed |  |  | Past deadline
ATTENTION | [5 empty] | NEXT UP
[6 empty] | When | Task | Room | Owner | Status
RECENT EXPENSES | [5 empty] | ROOMS
Date | Vendor | Description | Amount | Status |  | Room | Status | Budget | Spent | %
Kitchen
Living Room
Primary Bathroom
Guest Bedroom
Dining Room
Exterior / Garden
Laundry
Entry / Foyer
UPCOMING CONTRACTOR VISITS | [5 empty] | QUICK ACTIONS (use the Hearth & Timber menu in Google Sheets)
Date | Event | Owner | Status |  |  | + Expense
+ Task
Upload photo note
Message contractor
Approve change order
Generate shopping list
AI INSIGHT
NAVIGATION
Projects |  | Rooms |  | Design | Budget |  | Team |  | Materials
Tasks |  | Messages |  | Documents | Home |  | Maint. |  | Admin

## Projects
PROJECTS
All renovation projects · spent/committed roll up from Expenses
Project ID | Property ID | Name | Type | Status | Phase | Start | Target End | Actual End | Budget | Homeowner ID | PM ID | Designer ID | Homeowner Name | Address | Progress | Notes | Spent | Committed | Remaining | Health
PRJ-001 | PROP-001 | Maplewood Whole-Home Refresh | Whole Home | Active | Construction | 2026-03-01 | 2026-11-15 |  | 85000 | HO-001 | PM-001 | DS-001 | Alex Rivera | 1847 Maplewood Drive, Portland, OR | 72% | Kitchen, primary bath, living, guest bedroom, exterior paint, garden path.
PRJ-002 | PROP-002 | Gorge Cabin Bath Refresh | Bathroom | Planning | Design | 2026-10-01 | 2026-12-15 |  | 18500 | HO-001 | PM-001 | DS-001 | Alex Rivera | 88 Ridge Trail, Hood River, OR | 12% | Single bath + vanity lighting. Starts after Maplewood handover.

## Rooms
ROOMS
Every space is a node in the digital twin
Room ID | Project ID | Room Name | Type | Floor | Length (ft) | Width (ft) | Height (ft) | Condition | Status | Budget | Contractor ID | Design Style | Before Photos | After Photos | Notes | Area (sf) | Spent | Committed | Remaining | Budget used
RM-01 | PRJ-001 | Kitchen | Kitchen | 1 | 16 | 12.5 | 9 | Fair | In Progress | 32000 | CTR-001 | Modern | drive/photos/kitchen-before | drive/photos/kitchen-wip | Load-bearing wall stays. Island added.
RM-02 | PRJ-001 | Living Room | Living Room | 1 | 20 | 15 | 9.5 | Good | In Progress | 12500 | CTR-006 | Scandinavian | drive/photos/living-before |  | White oak floors continue from kitchen.
RM-03 | PRJ-001 | Primary Bathroom | Primary Bathroom | 2 | 10 | 8 | 8.5 | Poor | Punch List | 18500 | CTR-004 | Luxury | drive/photos/bath-before | drive/photos/bath-after-draft | Heated floor. Porcelain in lieu of marble.
RM-04 | PRJ-001 | Guest Bedroom | Bedroom | 2 | 12 | 11 | 8.5 | Fair | Design | 6200 | CTR-005 | Minimal | drive/photos/guest-before |  | Paint, lighting, built-in wardrobe.
RM-05 | PRJ-001 | Dining Room | Dining Room | 1 | 13 | 11 | 9.5 | Good | In Progress | 4800 | CTR-005 | Transitional | drive/photos/dining-before |  | Sconce pair + plaster repair.
RM-06 | PRJ-001 | Exterior / Garden | Exterior | 0 | 40 | 22 | 0 | Fair | Not Started | 7400 | CTR-010 | Traditional | drive/photos/exterior-before |  | Front path, porch stain, lighting.
RM-07 | PRJ-001 | Laundry | Laundry | 1 | 8 | 6 | 8.5 | Fair | Complete | 2100 | CTR-003 | Minimal | drive/photos/laundry-before | drive/photos/laundry-after | Utility sink and tile splash.
RM-08 | PRJ-001 | Entry / Foyer | Entry / Foyer | 1 | 8 | 7 | 9.5 | Good | In Progress | 1500 | CTR-005 | Transitional | drive/photos/entry-before |  | Bench, hook rail, paint.
RM-09 | PRJ-002 | Cabin Bathroom | Bathroom | 1 | 8 | 6.5 | 8 | Poor | Design | 18500 | CTR-004 | Scandinavian | drive/photos/cabin-bath-before |  | Full gut. Starts October.

## Design Studio
DESIGN STUDIO
Mood boards, palettes, materials, 2D/3D, AI concepts · style presets included
Design ID | Project ID | Room ID | Item Type | Name | Style | Brand | Color Hex | Link / File | Status | Cost Est. | AI Suggested | Notes
DSN-001 | PRJ-001 | RM-01 | Mood Board | Kitchen — warm modern | Modern |  | #16352F | drive/mood/kitchen-01 | Approved | 0 | No | Forest + sand + terracotta. Brass hardware.
DSN-002 | PRJ-001 | RM-01 | Color Palette | Kitchen palette v3 | Modern | Farrow & Ball | #E8DDCB | drive/palette/kitchen | Approved | 0 | Yes | AI suggested dropping cool gray for sand.
DSN-003 | PRJ-001 | RM-01 | Cabinetry | Shaker, painted sage | Modern | Cascade | #719B7A | drive/cabs/shaker-sage | Approved | 14800 | No | Inset doors, walnut island.
DSN-004 | PRJ-001 | RM-01 | Flooring | White oak 7in | Scandinavian | Timberline | #D4C6AE | drive/floor/oak | Installed | 4200 | No | Continues into living + dining.
DSN-005 | PRJ-001 | RM-01 | Lighting | Aged brass pendants x3 | Luxury | BrightPath | #C86B4A | drive/light/island | Ordered | 890 | No | Dimmer on island circuit.
DSN-006 | PRJ-001 | RM-03 | Material Board | Bath — porcelain in lieu of marble | Luxury | Heritage | #F8F6F1 | drive/bath/materials | Approved | 0 | Yes | AI: porcelain saves ~18% vs marble.
DSN-007 | PRJ-001 | RM-03 | AI Concept | Primary bath — spa luxury | Luxury |  |  | drive/ai/bath-luxury | Accepted | 0 | Yes | Before/after concept set.
DSN-008 | PRJ-001 | RM-02 | Mood Board | Living — Scandinavian calm | Scandinavian |  | #E8DDCB | drive/mood/living | Approved | 0 | No | Linen, oak, charcoal textiles.
DSN-009 | PRJ-001 | RM-02 | Furniture | Modular sofa + oak table | Scandinavian | Article | #202522 | drive/furn/living | Quoted | 3400 | No | Lead time 6 weeks — order by Sep 1.
DSN-010 | PRJ-001 | RM-04 | Color Palette | Guest — clay + linen | Minimal | Benjamin Moore | #C86B4A | drive/palette/guest | In Review | 0 | Yes | Two accent options pending Alex.
DSN-011 | PRJ-001 | RM-01 | 2D Floor Plan | Kitchen layout v4 | Modern | Luna |  | drive/plans/kitchen-v4 | Approved | 0 | No | Island 8ft. Fridge wall flipped.
DSN-012 | PRJ-001 | RM-01 | 3D Visualization | Kitchen dusk render | Modern | Luna |  | drive/3d/kitchen-dusk | Approved | 0 | Yes | AI lighting study included.
DSN-013 | PRJ-002 | RM-09 | Mood Board | Cabin bath — Japandi | Japandi |  | #16352F | drive/mood/cabin | Draft | 0 | Yes | Cedar, plaster, black fixtures.

## AI Insights
AI INSIGHTS
Renovation assistant · budget, materials, schedule, contractor comparison, photo analysis
Insight ID | Date | Project ID | Room ID | Category | Severity | Insight | Recommendation | Est. Impact $ | Status | Action Taken
AI-001 | 2026-08-20 | PRJ-001 | RM-01 | Budget | Warning | Kitchen renovation is currently 12% over the planned budget. | Switch remaining stone from marble to porcelain slab on the island only; keep quartz on perimeter. | 2100 | Accepted | Quote requested from Heritage Tile
AI-002 | 2026-08-18 | PRJ-001 | RM-03 | Materials | Opportunity | Porcelain tile alternative identified for primary bath floor. | Heritage porcelain (SKU HT-8841) matches the approved palette and saves ~18% versus marble. | 1640 | Resolved | Material swapped. Installed.
AI-003 | 2026-08-22 | PRJ-001 | RM-01 | Schedule | Warning | Cabinet installation is on the critical path and hardware is still in transit. | Confirm hardware ETA. If later than Aug 27, install doors without pulls and return for hardware day. | 0 | In Progress | Maya tracking shipment
AI-004 | 2026-08-15 | PRJ-001 |  | Contractor | Info | Three lighting bids received. Spread is 22%. | BrightPath is mid-price with the highest communication score. Accept unless value-engineering fixtures. | 340 | Accepted | BrightPath awarded
AI-005 | 2026-08-23 | PRJ-001 | RM-06 | Risk | Critical | Project contingency has fallen to 9.4%, below the 10% threshold. | Freeze non-critical exterior extras (water feature) until kitchen close-out. | 1800 | New
AI-006 | 2026-08-10 | PRJ-001 | RM-02 | Design | Opportunity | Room photo analysis: north-facing living room reads cool and dim after 4pm. | Specify 2700K lamps, add floor lamp at north corner, keep walls in Warm Sand not cool gray. | 0 | Resolved | Palette updated
AI-007 | 2026-08-21 | PRJ-001 |  | Procurement | Warning | White oak stair nosing is backordered 11 days. | Use matching leftover plank with site-cut nosing, or delay living-room furniture delivery. | 0 | Accepted | Site-cut nosing approved
AI-008 | 2026-08-24 | PRJ-001 |  | Prediction | Info | Likely completion date given current float: 12 Nov 2026 (3 days ahead of target). | Protect flooring cure time. Do not accelerate furniture move-in before Oct 20. | 0 | New

## Budget
BUDGET
Category + room budgets · spent/committed live from Expenses
Line ID | Project ID | Room ID | Category | Subcategory | Planned | Spent (Paid) | Committed | Remaining | Variance | Variance % | Alert
BL-001 | PRJ-001 | RM-01 | Materials | Cabinetry & hardware | 14800
BL-002 | PRJ-001 | RM-01 | Materials | Counters & backsplash | 6200
BL-003 | PRJ-001 | RM-01 | Materials | Appliances | 5400
BL-004 | PRJ-001 | RM-01 | Labor | Cabinet install + finish carpentry | 3600
BL-005 | PRJ-001 | RM-01 | Labor | Plumbing relocate | 1400
BL-006 | PRJ-001 | RM-01 | Labor | Electrical / lighting | 600
BL-007 | PRJ-001 | RM-02 | Materials | White oak flooring (share) | 2800
BL-008 | PRJ-001 | RM-02 | Labor | Floor install + finish | 2200
BL-009 | PRJ-001 | RM-02 | Furniture | Sofa, table, lighting | 4200
BL-010 | PRJ-001 | RM-02 | Materials | Paint & plaster | 900
BL-011 | PRJ-001 | RM-02 | Labor | Paint labor | 1400
BL-012 | PRJ-001 | RM-03 | Materials | Tile, fixtures, vanity | 9200
BL-013 | PRJ-001 | RM-03 | Labor | Tile + plumbing + electric | 6800
BL-014 | PRJ-001 | RM-03 | Materials | Heated floor system | 1800
BL-015 | PRJ-001 | RM-04 | Materials | Paint, lighting, wardrobe | 2800
BL-016 | PRJ-001 | RM-04 | Labor | Paint + carpentry | 2200
BL-017 | PRJ-001 | RM-04 | Furniture | Bed + textiles | 1200
BL-018 | PRJ-001 | RM-05 | Materials | Lighting + plaster | 1600
BL-019 | PRJ-001 | RM-05 | Labor | Paint + electric | 2000
BL-020 | PRJ-001 | RM-05 | Furniture | Dining table remainder | 1200
BL-021 | PRJ-001 | RM-06 | Materials | Path, stain, fixtures | 3400
BL-022 | PRJ-001 | RM-06 | Labor | Landscape + paint | 4000
BL-023 | PRJ-001 | RM-07 | Materials | Tile + sink | 900
BL-024 | PRJ-001 | RM-07 | Labor | Install | 1200
BL-025 | PRJ-001 | RM-08 | Materials | Bench + rail + paint | 700
BL-026 | PRJ-001 | RM-08 | Labor | Carpentry + paint | 800
BL-027 | PRJ-001 |  | Design | Luna Interiors retainer + hours | 4800
BL-028 | PRJ-001 |  | Permits | Building, electrical, plumbing | 1850
BL-029 | PRJ-001 |  | Delivery | Freight & white-glove | 900
BL-030 | PRJ-001 |  | Inspections | City + independent | 650
BL-031 | PRJ-001 |  | Contingency | 10% project reserve | 8500
BL-032 | PRJ-001 | RM-01 | Labor | Demolition (kitchen share) | 0
BL-033 | PRJ-001 |  | Labor | General contractor / PM | 6200
BL-034 | PRJ-002 | RM-09 | Materials | Cabin bath package | 9200
BL-035 | PRJ-002 | RM-09 | Labor | Gut and reset | 6800
BL-036 | PRJ-002 |  | Design | Concept + drawings | 1200
BL-037 | PRJ-002 |  | Contingency | 10% reserve | 1300
TOTAL (all lines)

## Expenses
EXPENSES
Every dollar · Planned / Committed / Paid · add rows below, keep Status valid
Expense ID | Date | Project ID | Room ID | Category | Vendor | Description | Amount | Method | Status | Receipt / Invoice | Approved By
EXP-001 | 2026-03-08 | PRJ-001 |  | Design | Luna Interiors | Design retainer | 2400 | ACH | Paid | INV-LUNA-110 | Alex Rivera
EXP-002 | 2026-04-02 | PRJ-001 |  | Permits | City of Portland | Building permit | 840 | Credit Card | Paid | PMT-2026-441 | Marcus Webb
EXP-003 | 2026-04-18 | PRJ-001 |  | Permits | City of Portland | Electrical + plumbing permits | 610 | Credit Card | Paid | PMT-2026-478 | Marcus Webb
EXP-004 | 2026-05-04 | PRJ-001 |  | Design | Luna Interiors | Drawings + 3D package | 1800 | ACH | Paid | INV-LUNA-126 | Alex Rivera
EXP-005 | 2026-05-22 | PRJ-001 |  | Labor | Ironwood Construction | Demolition + dumpsters | 2800 | Check | Paid | INV-IW-204 | Alex Rivera
EXP-006 | 2026-06-06 | PRJ-001 | RM-01 | Labor | Northwest Electric | Kitchen / bath rough-in | 1900 | ACH | Paid | INV-NWE-88 | Marcus Webb
EXP-007 | 2026-06-12 | PRJ-001 | RM-03 | Labor | Pacific Plumbing | Bath / laundry rough-in | 2400 | ACH | Paid | INV-PP-301 | Marcus Webb
EXP-008 | 2026-06-20 | PRJ-001 | RM-03 | Materials | Tile & Timber Co. | Porcelain floor + wall tile | 3180 | Credit Card | Paid | PO-114 | Sofia Alvarez
EXP-009 | 2026-06-28 | PRJ-001 | RM-03 | Materials | Ferguson | Bath fixtures package | 2140 | Credit Card | Paid | FERG-9921 | Sofia Alvarez
EXP-010 | 2026-07-02 | PRJ-001 | RM-03 | Materials | WarmFloor Co. | Heated floor kit | 1680 | Credit Card | Paid | WF-441 | Marcus Webb
EXP-011 | 2026-07-08 | PRJ-001 | RM-01 | Labor | Pacific Plumbing | Kitchen sink relocate | 1280 | ACH | Paid | INV-PP-318 | Marcus Webb
EXP-012 | 2026-07-15 | PRJ-001 | RM-03 | Labor | Heritage Tile & Stone | Primary bath tile labor (50%) | 2100 | ACH | Paid | INV-HT-77 | Marcus Webb
EXP-013 | 2026-07-18 | PRJ-001 | RM-07 | Materials | Tile & Timber Co. | Laundry tile + sink | 860 | Credit Card | Paid | PO-129 | Sofia Alvarez
EXP-014 | 2026-07-22 | PRJ-001 | RM-07 | Labor | Pacific Plumbing | Laundry install | 980 | ACH | Paid | INV-PP-330 | Marcus Webb
EXP-015 | 2026-07-28 | PRJ-001 | RM-01 | Materials | Timberline Floors | White oak 7in — kitchen/living/dining | 6400 | ACH | Paid | PO-140 | Sofia Alvarez
EXP-016 | 2026-08-02 | PRJ-001 | RM-01 | Materials | Cascade Cabinets | Cabinet deposit 50% | 7400 | Wire | Paid | INV-CC-501 | Alex Rivera
EXP-017 | 2026-08-05 | PRJ-001 | RM-02 | Labor | Timberline Floors | Floor install progress | 1800 | ACH | Paid | INV-TF-19 | Marcus Webb
EXP-018 | 2026-08-08 | PRJ-001 | RM-03 | Labor | Heritage Tile & Stone | Bath tile labor remainder | 2100 | ACH | Paid | INV-HT-81 | Marcus Webb
EXP-019 | 2026-08-10 | PRJ-001 | RM-03 | Labor | Pacific Plumbing | Bath trim-out | 1460 | ACH | Paid | INV-PP-341 | Marcus Webb
EXP-020 | 2026-08-12 | PRJ-001 |  | Inspections | City of Portland | Plumbing + electrical inspection | 240 | Credit Card | Paid | INSP-0812 | Marcus Webb
EXP-021 | 2026-08-14 | PRJ-001 | RM-01 | Materials | Sub-Zero / Wolf dealer | Range + fridge deposit | 2700 | Credit Card | Paid | APPL-01 | Alex Rivera
EXP-022 | 2026-08-16 | PRJ-001 | RM-01 | Materials | Caesarstone | Perimeter quartz | 2480 | Credit Card | Paid | CS-882 | Sofia Alvarez
EXP-023 | 2026-08-18 | PRJ-001 |  | Labor | Ironwood Construction | August PM / supervision | 1550 | ACH | Paid | INV-IW-228 | Alex Rivera
EXP-024 | 2026-08-20 | PRJ-001 | RM-01 | Delivery | Cascade Cabinets | Cabinet freight | 420 | Credit Card | Paid | FRT-88 | Maya Chen
EXP-025 | 2026-08-22 | PRJ-001 | RM-05 | Materials | BrightPath Lighting | Dining sconces | 380 | Credit Card | Paid | BP-204 | Sofia Alvarez
EXP-026 | 2026-08-25 | PRJ-001 | RM-01 | Materials | Cascade Cabinets | Cabinet balance | 7400 | Wire | Committed | INV-CC-502 | Alex Rivera
EXP-027 | 2026-08-28 | PRJ-001 | RM-01 | Labor | Cascade Cabinets | Install labor | 3600 | ACH | Committed | INV-CC-510 | Marcus Webb
EXP-028 | 2026-09-04 | PRJ-001 | RM-01 | Materials | Heritage Tile & Stone | Island porcelain slab | 1860 | Credit Card | Committed | PO-155 | Sofia Alvarez
EXP-029 | 2026-09-08 | PRJ-001 | RM-01 | Materials | BrightPath Lighting | Island pendants | 890 | Credit Card | Planned | BP-220 | Sofia Alvarez
EXP-030 | 2026-09-12 | PRJ-001 | RM-04 | Materials | Sherwin-Williams | Guest bedroom paint | 240 | Credit Card | Planned
EXP-031 | 2026-09-18 | PRJ-001 | RM-02 | Furniture | Article | Sofa + coffee table | 3400 | Credit Card | Planned |  | Sofia Alvarez
EXP-032 | 2026-10-02 | PRJ-001 | RM-06 | Materials | Garden & Gate | Path stone deposit | 1200 | Check | Planned
EXP-033 | 2026-08-01 | PRJ-002 |  | Design | Luna Interiors | Cabin bath concept | 600 | ACH | Paid | INV-LUNA-140 | Alex Rivera
EXP-034 | 2026-07-30 | PRJ-001 | RM-01 | Labor | Northwest Electric | Finish electrical progress | 720 | ACH | Paid | INV-NWE-97 | Marcus Webb
EXP-035 | 2026-08-19 | PRJ-001 | RM-08 | Materials | Rejuvenation | Hook rail + hooks | 186 | Credit Card | Paid | REJ-33 | Alex Rivera

## Finance
FINANCE
Financial dashboard · planned vs actual, by room, by category, by month
BUDGET (active project) |  |  | SPENT |  |  | COMMITTED |  |  | REMAINING
Total planned |  |  | Paid to date |  |  | Approved, not yet paid |  |  | Budget − spent − committed
% USED |  |  | CONTINGENCY LEFT |  |  | THIS MONTH SPENT |  |  | HEALTH
Spent + committed |  |  | Watch the 10% floor |  |  | Paid in current month |  |  | Vs overrun threshold
Cost by category | [6 empty] | Cost by room (active project)
Category | Planned | Spent | Committed | Remaining | % Used |  | Room | Budget | Spent | Committed | Remaining | % Used
Labor | [6 empty] | Kitchen
Materials | [6 empty] | Living Room
Design | [6 empty] | Primary Bathroom
Permits | [6 empty] | Guest Bedroom
Delivery | [6 empty] | Dining Room
Contingency | [6 empty] | Exterior / Garden
Appliances | [6 empty] | Laundry
Furniture | [6 empty] | Entry / Foyer
Inspections
Other
Monthly spending (paid)
Month | Spent | Committed dated |  |  |  |  | Smart alerts
Mar 2026
Apr 2026
May 2026
Jun 2026
Jul 2026
Aug 2026
Sep 2026
Oct 2026
Nov 2026

## Contractors
CONTRACTORS
Profiles, insurance, licenses · Score = average of Quality / On-time / Budget / Communication
Contractor ID | Company | Contact | Trade | Skills | Phone | Email | Rating | Quality | On-Time | Budget | Communication | Score | Insurance Exp | License | Availability | Rate ($/hr) | Status | Portfolio
CTR-001 | Cascade Cabinets | Maya Chen | Cabinetry | Custom millwork, inset doors | +1-503-555-0111 | maya@cascadecabinets.example | 4.8 | 92% | 87% | 95% | 90% |  | 2027-03-01 | CCB-210998 | Aug 20–Sep 15 | 85 | Active | drive/portfolio/cascade
CTR-002 | Northwest Electric | Jordan Hale | Electrical | Residential remodel, lighting | +1-503-555-0133 | jordan@nw-electric.example | 4.7 | 94% | 91% | 88% | 86% |  | 2026-12-15 | EL-44821 | On call | 110 | Active | drive/portfolio/nwe
CTR-003 | Pacific Plumbing | Sam Ortiz | Plumbing | Repipe, fixtures, radiant | +1-503-555-0140 | sam@pacificplumbing.example | 4.6 | 90% | 84% | 93% | 88% |  | 2027-01-20 | PL-77310 | Wrap this week | 120 | Active | drive/portfolio/pp
CTR-004 | Heritage Tile & Stone | Priya Shah | Tile & Stone | Porcelain, slab, steam | +1-503-555-0155 | priya@heritagetile.example | 4.9 | 96% | 89% | 91% | 93% |  | 2027-06-01 | CCB-188442 | Punch list | 95 | Active | drive/portfolio/heritage
CTR-005 | Greenfield Painting | Leo Park | Painting | Plaster, limewash, cabinets | +1-503-555-0122 | leo@greenfieldpaint.example | 4.5 | 88% | 90% | 86% | 91% |  | 2026-11-30 | CCB-201774 | Sep 10–28 | 65 | Active | drive/portfolio/greenfield
CTR-006 | Timberline Floors | Elena Voss | Flooring | White oak, site finish | +1-503-555-0166 | elena@timberlinefloors.example | 4.7 | 91% | 83% | 90% | 87% |  | 2027-02-14 | CCB-176330 | Through Aug 28 | 8 | Active | drive/portfolio/timberline
CTR-007 | Luna Interiors | Sofia Alvarez | Interior Designer | Residential, kitchen, bath | +1-503-555-0194 | sofia@lunainteriors.example | 4.9 | 95% | 94% | 89% | 97% |  | 2026-10-01 | ASID-4491 | Ongoing | 145 | Active | drive/portfolio/luna
CTR-008 | Ironwood Construction | Marcus Webb | General Contractor | Remodel GC, historic homes | +1-503-555-0172 | marcus@ironwood.build | 4.8 | 93% | 88% | 92% | 94% |  | 2027-04-30 | CCB-154009 | Full project | 0 | Active | drive/portfolio/ironwood
CTR-009 | BrightPath Lighting | Nina Cho | Lighting | Specification + supply | +1-503-555-0180 | nina@brightpath.example | 4.6 | 90% | 92% | 94% | 89% |  | 2026-09-30 | SUP-8891 | Lead time 3 wks | 0 | Active | drive/portfolio/brightpath
CTR-010 | Garden & Gate | Theo Brooks | Landscaping | Paths, planting, irrigation | +1-503-555-0199 | theo@gardengate.example | 4.4 | 86% | 80% | 88% | 85% |  | 2027-05-01 | LCB-3320 | Oct window | 70 | Active | drive/portfolio/gg
CTR-011 | Alder Inspection Group | Riley Grant | Inspection | Independent punch | +1-503-555-0188 | riley@alderinspect.example | 4.8 | 97% | 95% | 100% | 90% |  | 2026-12-31 | OR-INSP-220 | On call | 175 | Active

## Quotes
QUOTES
Request → receive → compare → award
Quote ID | Project ID | Room ID | Contractor ID | Trade | Scope | Amount | Timeline (days) | Valid Until | Status | Notes
Q-001 | PRJ-001 | RM-01 | CTR-001 | Cabinetry | Full kitchen millwork — sage shaker + walnut island | 14800 | 18 | 2026-05-30 | Accepted | Awarded. Deposit paid.
Q-002 | PRJ-001 | RM-01 | CTR-001 | Cabinetry | Alternate: all walnut | 18600 | 22 | 2026-05-30 | Rejected | Over palette and budget.
Q-003 | PRJ-001 | RM-03 | CTR-004 | Tile & Stone | Marble floor + shower | 9100 | 14 | 2026-05-20 | Rejected | AI flagged 18% save with porcelain.
Q-004 | PRJ-001 | RM-03 | CTR-004 | Tile & Stone | Porcelain floor + shower + slab niche | 7460 | 12 | 2026-05-20 | Accepted | Selected.
Q-005 | PRJ-001 |  | CTR-009 | Lighting | Whole-home spec package | 4120 | 21 | 2026-06-15 | Accepted | Best communication score.
Q-006 | PRJ-001 |  | CTR-009 | Lighting | Competitor A package | 3680 | 28 | 2026-06-15 | Compared | Cheaper, slower, weaker spec.
Q-007 | PRJ-001 |  | CTR-009 | Lighting | Competitor B package | 4490 | 18 | 2026-06-15 | Compared | Premium, not needed.
Q-008 | PRJ-001 | RM-02 | CTR-006 | Flooring | White oak supply + install | 8600 | 16 | 2026-06-01 | Accepted | Shared across 3 rooms.
Q-009 | PRJ-001 | RM-06 | CTR-010 | Landscaping | Path + planting + lighting | 7400 | 12 | 2026-09-15 | Received | Hold extras until contingency recovers.
Q-010 | PRJ-002 | RM-09 | CTR-004 | Tile & Stone | Cabin bath tile package | 5400 | 10 | 2026-10-30 | Requested

## Jobs
JOBS
Assigned work, milestones, balances
Job ID | Project ID | Room ID | Contractor ID | Quote ID | Scope | Start | End | Milestone | Status | Amount | Paid | Balance | % Paid
JOB-001 | PRJ-001 |  | CTR-008 | Q-000 | GC / project management | 2026-03-01 | 2026-11-15 | Monthly supervision | In Progress | 6200 | 4350
JOB-002 | PRJ-001 | RM-01 | CTR-001 | Q-001 | Kitchen cabinetry fabricate + install | 2026-08-20 | 2026-09-15 | Boxes set; doors next | In Progress | 18400 | 7400
JOB-003 | PRJ-001 | RM-03 | CTR-004 | Q-004 | Primary bath tile | 2026-07-08 | 2026-08-12 | Complete — punch remaining | Milestone Review | 7460 | 7460
JOB-004 | PRJ-001 | RM-01 | CTR-002 | Q-000 | Electrical rough + finish | 2026-06-01 | 2026-09-20 | Finish pending cabinets | In Progress | 2620 | 2620
JOB-005 | PRJ-001 | RM-03 | CTR-003 | Q-000 | Plumbing rough + trim | 2026-06-08 | 2026-08-14 | Trim complete | Complete | 5140 | 5140
JOB-006 | PRJ-001 | RM-02 | CTR-006 | Q-008 | Flooring install | 2026-08-05 | 2026-08-28 | Sand/finish this week | In Progress | 8600 | 8200
JOB-007 | PRJ-001 |  | CTR-007 | Q-000 | Interior design services | 2026-03-01 | 2026-11-01 | FF&E procurement | In Progress | 4800 | 4200
JOB-008 | PRJ-001 | RM-04 | CTR-005 | Q-000 | Paint guest + dining + entry | 2026-09-10 | 2026-09-28 | Scheduled | Scheduled | 3600 | 0
JOB-009 | PRJ-001 | RM-06 | CTR-010 | Q-009 | Exterior path + porch | 2026-10-06 | 2026-10-24 | Not released | Assigned | 7400 | 0
JOB-010 | PRJ-001 |  | CTR-009 | Q-005 | Lighting supply | 2026-07-01 | 2026-09-20 | Pendants in transit | In Progress | 4120 | 380

## Tasks
TASKS
Kanban fields · To Do → Scheduled → In Progress → Inspection → Completed
Task ID | Project ID | Room ID | Title | Description | Assignee | Role | Status | Priority | Start | Deadline | Cost | Depends On | % Complete | Attachments / Comments | Days Left | Health
TSK-001 | PRJ-001 |  | Kickoff + scope lock | Confirm rooms, budget, style. | Marcus Webb | Project Manager | Completed | High | 2026-03-01 | 2026-03-08 | 0 |  | 100% | drive/notes/kickoff
TSK-002 | PRJ-001 | RM-01 | Kitchen measured drawings | Field measure + as-builts. | Sofia Alvarez | Interior Designer | Completed | High | 2026-03-10 | 2026-03-20 | 0 |  | 100%
TSK-003 | PRJ-001 |  | Submit building permit | Packet to City of Portland. | Marcus Webb | Project Manager | Completed | Critical | 2026-04-01 | 2026-04-10 | 840 |  | 100%
TSK-004 | PRJ-001 | RM-01 | Kitchen demolition | Cabinets, floor, plaster. | Marcus Webb | Project Manager | Completed | High | 2026-05-21 | 2026-06-05 | 2800 | TSK-003 | 100% | drive/photos/demo
TSK-005 | PRJ-001 | RM-01 | Electrical rough-in | New circuits, island, lighting. | Jordan Hale | Subcontractor | Completed | High | 2026-06-01 | 2026-06-20 | 1900 | TSK-004 | 100%
TSK-006 | PRJ-001 | RM-03 | Plumbing rough-in | Bath + laundry + kitchen stub. | Sam Ortiz | Contractor | Completed | High | 2026-06-08 | 2026-06-28 | 2400 | TSK-004 | 100%
TSK-007 | PRJ-001 | RM-03 | Heated floor install | WarmFloor mat + thermostat. | Sam Ortiz | Contractor | Completed | Medium | 2026-07-02 | 2026-07-06 | 1680 | TSK-006 | 100%
TSK-008 | PRJ-001 | RM-03 | Tile primary bath | Floor, shower, niche. | Priya Shah | Contractor | Completed | High | 2026-07-08 | 2026-08-08 | 4200 | TSK-007 | 100%
TSK-009 | PRJ-001 | RM-03 | Bath fixture trim | Valve trims, vanity, toilet, glass. | Sam Ortiz | Contractor | Completed | High | 2026-08-09 | 2026-08-14 | 1460 | TSK-008 | 100%
TSK-010 | PRJ-001 | RM-03 | Primary bath punch | Silicone, grout haze, door align. | Priya Shah | Contractor | Inspection | Medium | 2026-08-18 | 2026-08-26 | 0 | TSK-009 | 80%
TSK-011 | PRJ-001 | RM-07 | Laundry complete | Tile splash + utility sink. | Sam Ortiz | Contractor | Completed | Low | 2026-07-18 | 2026-07-24 | 1840 |  | 100%
TSK-012 | PRJ-001 | RM-01 | White oak flooring | Install kitchen/living/dining. | Elena Voss | Contractor | In Progress | Critical | 2026-08-05 | 2026-08-28 | 8200 | TSK-005 | 75%
TSK-013 | PRJ-001 | RM-01 | Cabinet box set | Set boxes, scribe, level island. | Maya Chen | Contractor | In Progress | Critical | 2026-08-20 | 2026-08-27 | 0 | TSK-012 | 55%
TSK-014 | PRJ-001 | RM-01 | Cabinet doors + hardware | Hang doors, install pulls. | Maya Chen | Contractor | Scheduled | Critical | 2026-08-28 | 2026-09-05 | 0 | TSK-013 | 0% | Hardware in transit
TSK-015 | PRJ-001 | RM-01 | Counter template | Quartz + island porcelain. | Heritage Tile | Contractor | Scheduled | High | 2026-09-04 | 2026-09-04 | 0 | TSK-014 | 0%
TSK-016 | PRJ-001 | RM-01 | Counter install | Set, seam, sink. | Heritage Tile | Contractor | To Do | High | 2026-09-10 | 2026-09-11 | 1860 | TSK-015 | 0%
TSK-017 | PRJ-001 | RM-01 | Appliance delivery | Range, fridge, DW. | Alex Rivera | Homeowner | Scheduled | High | 2026-09-12 | 2026-09-12 | 2700 | TSK-016 | 0%
TSK-018 | PRJ-001 | RM-01 | Island pendant hang | Three aged-brass pendants. | Nina Cho | Supplier | To Do | Medium | 2026-09-16 | 2026-09-16 | 890 | TSK-017 | 0%
TSK-019 | PRJ-001 | RM-04 | Guest bedroom paint | Clay + linen palette. | Leo Park | Contractor | Scheduled | Medium | 2026-09-10 | 2026-09-16 | 240 |  | 0% | Awaiting palette lock
TSK-020 | PRJ-001 | RM-05 | Dining plaster + paint | Repair north wall, paint. | Leo Park | Contractor | Scheduled | Medium | 2026-09-17 | 2026-09-22 | 0 |  | 0%
TSK-021 | PRJ-001 | RM-08 | Entry bench + rail | White oak bench, brass hooks. | Marcus Webb | Project Manager | In Progress | Low | 2026-08-18 | 2026-08-29 | 186 |  | 40%
TSK-022 | PRJ-001 | RM-02 | Living furniture order | Sofa + table. 6-week lead. | Sofia Alvarez | Interior Designer | To Do | High | 2026-09-01 | 2026-09-01 | 3400 |  | 0% | Order by Sep 1
TSK-023 | PRJ-001 | RM-06 | Exterior path layout | Stake path, confirm stone. | Theo Brooks | Contractor | To Do | Low | 2026-10-06 | 2026-10-08 | 0 |  | 0% | Hold extras
TSK-024 | PRJ-001 |  | Final city inspection | Building final. | Riley Grant | Inspector | To Do | Critical | 2026-10-25 | 2026-11-05 | 175 | TSK-018 | 0%
TSK-025 | PRJ-001 |  | Homeowner walkthrough | Punch list + handover packet. | Marcus Webb | Project Manager | To Do | High | 2026-11-10 | 2026-11-15 | 0 | TSK-024 | 0%
TSK-026 | PRJ-001 | RM-01 | Approve island slab | Confirm porcelain vs leftover quartz. | Alex Rivera | Homeowner | In Progress | High | 2026-08-22 | 2026-08-25 | 0 | AI-001 | 50% | Pending approval
TSK-027 | PRJ-001 |  | Weekly site meeting | GC + designer + homeowner. | Marcus Webb | Project Manager | Scheduled | Medium | 2026-08-25 | 2026-08-25 | 0 |  | 0% | Tue 9:00
TSK-028 | PRJ-002 | RM-09 | Cabin bath concept | Japandi mood board lock. | Sofia Alvarez | Interior Designer | In Progress | Low | 2026-08-01 | 2026-09-15 | 600 |  | 40%
TSK-029 | PRJ-001 | RM-01 | Backsplash layout | Zellige sample on site. | Sofia Alvarez | Interior Designer | Scheduled | Medium | 2026-09-08 | 2026-09-09 | 0 | TSK-016 | 0%
TSK-030 | PRJ-001 |  | Update insurance inventory | Photograph new fixtures. | Alex Rivera | Homeowner | To Do | Medium | 2026-11-12 | 2026-11-14 | 0 | TSK-025 | 0%

## Timeline
TIMELINE
Phase schedule · Gantt to the right · each block is one week from 1 Mar 2026
WEEKLY GANTT · filled cell = phase is active that week · gold column = this week
Phase ID | Project ID | Phase | Start | End | Duration (days) | Status | Depends On | % Elapsed | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21 | 2026-06-28 | 2026-07-05 | 2026-07-12 | 2026-07-19 | 2026-07-26 | 2026-08-02 | 2026-08-09 | 2026-08-16 | 2026-08-23 | 2026-08-30 | 2026-09-06 | 2026-09-13 | 2026-09-20 | 2026-09-27 | 2026-10-04 | 2026-10-11 | 2026-10-18 | 2026-10-25 | 2026-11-01 | 2026-11-08 | 2026-11-15 | 2026-11-22 | 2026-11-29
PH-01 | PRJ-001 | Planning | 2026-03-01 | 2026-03-31 |  | Completed
PH-02 | PRJ-001 | Design | 2026-03-15 | 2026-05-15 |  | Completed | PH-01
PH-03 | PRJ-001 | Permits | 2026-04-01 | 2026-05-20 |  | Completed | PH-01
PH-04 | PRJ-001 | Demolition | 2026-05-21 | 2026-06-05 |  | Completed | PH-03
PH-05 | PRJ-001 | Electrical | 2026-06-01 | 2026-07-10 |  | Completed | PH-04
PH-06 | PRJ-001 | Plumbing | 2026-06-08 | 2026-07-20 |  | Completed | PH-04
PH-07 | PRJ-001 | Walls / plaster | 2026-07-15 | 2026-08-10 |  | Completed | PH-05
PH-08 | PRJ-001 | Flooring | 2026-08-05 | 2026-08-28 |  | In Progress | PH-07
PH-09 | PRJ-001 | Cabinetry | 2026-08-20 | 2026-09-15 |  | In Progress | PH-08
PH-10 | PRJ-001 | Counters / appliances | 2026-09-10 | 2026-09-18 |  | Scheduled | PH-09
PH-11 | PRJ-001 | Painting | 2026-09-10 | 2026-09-28 |  | Scheduled | PH-07
PH-12 | PRJ-001 | Furniture | 2026-09-25 | 2026-10-20 |  | To Do | PH-11
PH-13 | PRJ-001 | Exterior / garden | 2026-10-06 | 2026-10-24 |  | To Do | PH-11
PH-14 | PRJ-001 | Final inspection | 2026-10-25 | 2026-11-05 |  | To Do | PH-12
PH-15 | PRJ-001 | Handover | 2026-11-10 | 2026-11-15 |  | To Do | PH-14
PH-16 | PRJ-002 | Cabin design | 2026-08-01 | 2026-09-30 |  | In Progress
PH-17 | PRJ-002 | Cabin construction | 2026-10-15 | 2026-12-10 |  | To Do | PH-16

## Materials
MATERIALS
Procurement · Required → Quoted → Approved → Ordered → Shipped → Delivered → Installed
Material ID | Project ID | Room ID | Product | Brand | SKU | Category | Qty Required | Unit | Unit Price | Line Total | Supplier | Qty Ordered | Qty Delivered | Qty Installed | Status | Warranty (mo) | Receipt | Order Date | Delivery Date | QR / Barcode | Open Qty
MAT-001 | PRJ-001 | RM-01 | Shaker cabinet box set | Cascade | CC-SH-Sage | Cabinetry | 1 | set | 14800 |  | Cascade Cabinets | 1 | 1 | 0.6 | Delivered | 60 | INV-CC-501 | 2026-06-01 | 2026-08-20 | QR-CC-001
MAT-002 | PRJ-001 | RM-01 | Aged brass bar pulls | Rejuvenation | RJ-BP-128 | Hardware | 28 | ea | 18 |  | Rejuvenation | 28 | 0 | 0 | Shipped | 12 |  | 2026-08-10 |  | QR-RJ-128
MAT-003 | PRJ-001 | RM-01 | White oak 7in engineered | Timberline | TL-WO-7 | Flooring | 780 | sf | 8.2 |  | Timberline Floors | 780 | 780 | 620 | Installed | 25 | PO-140 | 2026-07-01 | 2026-07-28 | QR-TL-WO7
MAT-004 | PRJ-001 | RM-01 | Perimeter quartz — Frost | Caesarstone | CS-5110 | Counters | 42 | sf | 59 |  | Caesarstone | 42 | 42 | 0 | Delivered | 15 | CS-882 | 2026-08-01 | 2026-08-16 | QR-CS-5110
MAT-005 | PRJ-001 | RM-01 | Island porcelain slab | Heritage | HT-8841 | Counters | 28 | sf | 66.4 |  | Heritage Tile & Stone | 0 | 0 | 0 | Approved | 25 |  |  |  | QR-HT-8841
MAT-006 | PRJ-001 | RM-01 | Zellige backsplash — sand | Cle | CLE-Z-14 | Tile | 48 | sf | 28 |  | Tile & Timber Co. | 0 | 0 | 0 | Quoted | 0 |  |  |  | QR-CLE-14
MAT-007 | PRJ-001 | RM-01 | Island pendants x3 | BrightPath | BP-ISL-AB | Lighting | 3 | ea | 296.67 |  | BrightPath Lighting | 3 | 0 | 0 | Ordered | 24 | BP-220 | 2026-08-18 |  | QR-BP-ISL
MAT-008 | PRJ-001 | RM-01 | Range 36in dual fuel | Wolf | DF364C | Appliances | 1 | ea | 0 |  | Sub-Zero / Wolf | 1 | 0 | 0 | Ordered | 24 | APPL-01 | 2026-08-14 |  | QR-WF-DF
MAT-009 | PRJ-001 | RM-01 | Counter-depth fridge | Sub-Zero | DEC3650 | Appliances | 1 | ea | 0 |  | Sub-Zero / Wolf | 1 | 0 | 0 | Ordered | 24 | APPL-01 | 2026-08-14 |  | QR-SZ-3650
MAT-010 | PRJ-001 | RM-03 | Porcelain floor 12x24 | Heritage | HT-8841F | Tile | 90 | sf | 14.2 |  | Tile & Timber Co. | 95 | 95 | 90 | Installed | 25 | PO-114 | 2026-06-10 | 2026-06-20 | QR-HT-F
MAT-011 | PRJ-001 | RM-03 | Shower wall porcelain | Heritage | HT-8841W | Tile | 110 | sf | 16.8 |  | Tile & Timber Co. | 115 | 115 | 110 | Installed | 25 | PO-114 | 2026-06-10 | 2026-06-20 | QR-HT-W
MAT-012 | PRJ-001 | RM-03 | Thermostatic shower set | Brizo | BZ-T600 | Fixtures | 1 | set | 890 |  | Ferguson | 1 | 1 | 1 | Installed | 60 | FERG-9921 | 2026-06-15 | 2026-06-28 | QR-BZ-T600
MAT-013 | PRJ-001 | RM-03 | Vanity 48in white oak | Cascade | CC-VAN-48 | Cabinetry | 1 | ea | 1680 |  | Cascade Cabinets | 1 | 1 | 1 | Installed | 24 | INV-CC-440 | 2026-07-01 | 2026-07-20 | QR-CC-VAN
MAT-014 | PRJ-001 | RM-03 | Heated floor kit | WarmFloor | WF-240-40 | Electrical | 1 | kit | 1680 |  | WarmFloor Co. | 1 | 1 | 1 | Installed | 36 | WF-441 | 2026-06-20 | 2026-07-02 | QR-WF-240
MAT-015 | PRJ-001 | RM-02 | Modular sofa | Article | ART-SVEN | Furniture | 1 | ea | 2400 |  | Article | 0 | 0 | 0 | Quoted | 12 |  |  |  | QR-ART-SV
MAT-016 | PRJ-001 | RM-02 | Oak coffee table | Article | ART-OAK-CT | Furniture | 1 | ea | 1000 |  | Article | 0 | 0 | 0 | Quoted | 12 |  |  |  | QR-ART-CT
MAT-017 | PRJ-001 | RM-05 | Dining sconces | BrightPath | BP-SCN-02 | Lighting | 2 | ea | 190 |  | BrightPath Lighting | 2 | 2 | 0 | Delivered | 24 | BP-204 | 2026-08-01 | 2026-08-22 | QR-BP-SCN
MAT-018 | PRJ-001 | RM-08 | Hook rail 48in | Rejuvenation | RJ-HR-48 | Hardware | 1 | ea | 186 |  | Rejuvenation | 1 | 1 | 0 | Delivered | 12 | REJ-33 | 2026-08-12 | 2026-08-19 | QR-RJ-HR
MAT-019 | PRJ-001 | RM-04 | Interior paint — Clay | Benjamin Moore | BM-HC-50 | Paint | 4 | gal | 62 |  | Sherwin-Williams | 0 | 0 | 0 | Required | 0 |  |  |  | QR-BM-CLAY
MAT-020 | PRJ-001 | RM-06 | Bluestone path pavers | Garden & Gate | GG-BLU-12 | Hardscape | 220 | sf | 9.5 |  | Garden & Gate | 0 | 0 | 0 | Quoted | 0 |  |  |  | QR-GG-BLU
MAT-021 | PRJ-001 | RM-01 | Undermount sink | Kohler | K-5285 | Fixtures | 1 | ea | 420 |  | Ferguson | 1 | 1 | 0 | Delivered | 36 | FERG-1002 | 2026-08-01 | 2026-08-12 | QR-K-5285
MAT-022 | PRJ-001 | RM-01 | Bridge faucet — brass | Brizo | BZ-K610 | Fixtures | 1 | ea | 640 |  | Ferguson | 1 | 0 | 0 | Shipped | 60 | FERG-1002 | 2026-08-08 |  | QR-BZ-K610
MAT-023 | PRJ-001 | RM-02 | Stair nosing — white oak | Timberline | TL-NOS-WO | Flooring | 14 | lf | 22 |  | Timberline Floors | 14 | 0 | 0 | Backordered | 25 |  | 2026-08-06 |  | QR-TL-NOS
MAT-024 | PRJ-002 | RM-09 | Cedar vanity | Cascade | CC-CED-36 | Cabinetry | 1 | ea | 2100 |  | Cascade Cabinets | 0 | 0 | 0 | Required | 24 |  |  |  | QR-CC-CED
MAT-025 | PRJ-001 | RM-04 | Wardrobe kit | IKEA / custom face | PAX-WO | Cabinetry | 1 | set | 890 |  | IKEA | 0 | 0 | 0 | Required | 12 |  |  |  | QR-PAX

## Shopping List
SHOPPING LIST
Auto-built from Materials still Required / Quoted / Approved · refresh by editing Materials
SKU / QR | Product | Room | Qty | Unit | Est. Unit $ | Est. Total | Supplier | Status | Project
Excel 365 and Google Sheets will spill the shopping list from row 5. If you are on Excel 2019 or earlier, filter the Materials sheet for Status = Required / Quoted / Approved and copy those rows here.

## Suppliers
SUPPLIERS
Vendor book · lead times drive the prediction engine
Supplier ID | Name | Category | Contact | Phone | Email | Website | Rating | Payment Terms | Lead Time (days) | Notes
SUP-001 | Tile & Timber Co. | Tile / flooring | Harper Quinn | +1-503-555-0160 | orders@tileandtimber.example | tileandtimber.example | 4.7 | Net 15 | 7 | Preferred tile house
SUP-002 | Ferguson | Plumbing fixtures | Counter desk | +1-503-555-2000 | pdx@ferguson.example | ferguson.com | 4.5 | Net 30 | 10 | Will-call available
SUP-003 | Caesarstone | Counters | West desk | +1-800-555-0199 | west@caesarstone.example | caesarstoneus.com | 4.6 | Prepaid | 14 | Frost 5110 in stock
SUP-004 | Sub-Zero / Wolf dealer | Appliances | Aiden Brooks | +1-503-555-2111 | aiden@swdealer.example | subzero-wolf.com | 4.8 | 50% deposit | 28 | Delivery window Sep 12
SUP-005 | Rejuvenation | Hardware / lighting | Online + Pearl | +1-888-401-1900 | hello@rejuvenation.example | rejuvenation.com | 4.6 | Card | 12 | Hardware in transit
SUP-006 | Sherwin-Williams | Paint | Hawthorne store | +1-503-555-2220 | store@sw.example | sherwin-williams.com | 4.4 | Card | 1 | Color match BM
SUP-007 | Article | Furniture | Wholesale desk | +1-888-746-3455 | trade@article.example | article.com | 4.3 | Prepaid | 42 | Order by Sep 1
SUP-008 | WarmFloor Co. | Radiant | Support | +1-800-555-0182 | support@warmfloor.example | warmfloor.example | 4.5 | Card | 5 | 10yr warranty
SUP-009 | BrightPath Lighting | Lighting | Nina Cho | +1-503-555-0180 | nina@brightpath.example | brightpath.example | 4.6 | Net 15 | 21 | Also a contractor
SUP-010 | Garden & Gate Yard | Hardscape | Theo Brooks | +1-503-555-0199 | yard@gardengate.example | gardengate.example | 4.4 | 50% deposit | 14 | Bluestone seasonal

## Documents
DOCUMENTS
Project vault · contracts, permits, warranties, photos, signed agreements
Doc ID | Project ID | Room ID | Category | Title | Version | File Link | Upload Date | Expiration | Signed | Owner | Notes | Days to Expiry | Expiry Alert
DOC-001 | PRJ-001 |  | Contract | Ironwood GC agreement | 1.2 | drive/docs/iw-contract.pdf | 2026-03-04 |  | Yes | Alex Rivera | Signed via DocuSign
DOC-002 | PRJ-001 |  | Contract | Luna Interiors design services | 1.0 | drive/docs/luna-contract.pdf | 2026-03-06 |  | Yes | Alex Rivera
DOC-003 | PRJ-001 | RM-01 | Contract | Cascade Cabinets millwork | 1.1 | drive/docs/cascade-contract.pdf | 2026-05-28 |  | Yes | Alex Rivera | Includes install
DOC-004 | PRJ-001 |  | Building Permit | Residential remodel permit | 1.0 | drive/docs/permit-441.pdf | 2026-04-12 | 2027-04-12 | Yes | Marcus Webb | Expires 12 months
DOC-005 | PRJ-001 |  | License | Ironwood CCB + insurance cert | 2026 | drive/docs/iw-insurance.pdf | 2026-03-04 | 2027-04-30 | No | Marcus Webb | Remind 30 days prior
DOC-006 | PRJ-001 | RM-01 | Floor Plan | Kitchen layout v4 | 4.0 | drive/plans/kitchen-v4.pdf | 2026-05-10 |  | Yes | Sofia Alvarez | Supersedes v3
DOC-007 | PRJ-001 | RM-03 | Floor Plan | Primary bath plan | 2.0 | drive/plans/bath-v2.pdf | 2026-05-12 |  | Yes | Sofia Alvarez
DOC-008 | PRJ-001 |  | Inspection Report | Plumbing rough inspection | 1.0 | drive/insp/plumb-rough.pdf | 2026-06-30 |  | No | Riley Grant | Pass
DOC-009 | PRJ-001 |  | Inspection Report | Electrical rough inspection | 1.0 | drive/insp/elec-rough.pdf | 2026-07-02 |  | No | Riley Grant | Pass
DOC-010 | PRJ-001 | RM-03 | Warranty | Heritage tile labor + material | 1.0 | drive/warr/heritage.pdf | 2026-08-12 | 2028-08-12 | No | Priya Shah | 2 year labor
DOC-011 | PRJ-001 | RM-03 | Product Manual | WarmFloor thermostat | 1.0 | drive/manuals/wf.pdf | 2026-07-06 |  | No | Sam Ortiz
DOC-012 | PRJ-001 | RM-01 | Invoice | Cascade deposit INV-CC-501 | 1.0 | drive/inv/cc-501.pdf | 2026-08-02 |  | No | Jamie Cole | Paid
DOC-013 | PRJ-001 | RM-01 | Photo | Kitchen before set | 1.0 | drive/photos/kitchen-before | 2026-03-12 |  | No | Alex Rivera | 20 images
DOC-014 | PRJ-001 |  | Insurance | Homeowner policy declarations | 2026 | drive/docs/ho-policy.pdf | 2026-01-05 | 2027-01-05 | No | Alex Rivera | Notify carrier of remodel
DOC-015 | PRJ-001 |  | Change Order | CO-002 island porcelain | 1.0 | drive/co/co-002.pdf | 2026-08-21 |  | No | Alex Rivera | Awaiting signature
DOC-016 | PRJ-002 | RM-09 | Photo | Cabin bath before | 1.0 | drive/photos/cabin-before | 2026-07-30 |  | No | Alex Rivera

## Messages
MESSAGES
Homeowner ↔ contractor ↔ designer ↔ supplier · keep threads on a room or task
Msg ID | Date / Time | Project ID | Room / Task | From | To | Channel | Message | Attachments | Mentions | Read
MSG-001 | 2026-08-20 09:12 | PRJ-001 | RM-01 / TSK-013 | Maya Chen | Alex Rivera | App | Boxes land tomorrow 7:30. Please keep driveway clear. |  | @Alex | Yes
MSG-002 | 2026-08-20 09:40 | PRJ-001 | RM-01 / TSK-013 | Alex Rivera | Maya Chen | App | Confirmed. I'll move the car tonight. |  | @Maya | Yes
MSG-003 | 2026-08-21 14:05 | PRJ-001 | RM-01 | Sofia Alvarez | Project group | Group Chat | AI recommends porcelain on the island only. Mood board updated. | drive/mood/kitchen-01 | @Alex @Marcus | Yes
MSG-004 | 2026-08-21 16:22 | PRJ-001 | RM-01 | Alex Rivera | Sofia Alvarez | App | Approved — keep quartz on the run, porcelain on the island. |  | @Sofia | Yes
MSG-005 | 2026-08-22 08:01 | PRJ-001 | MAT-002 | Maya Chen | Marcus Webb | SMS | Pulls still in transit. ETA Friday. Plan hardware day next week. |  | @Marcus | Yes
MSG-006 | 2026-08-22 11:18 | PRJ-001 | RM-03 / TSK-010 | Priya Shah | Alex Rivera | Photo Comment | Haze on the niche shelf — will reclean Thursday. | drive/photos/bath-niche | @Alex | Yes
MSG-007 | 2026-08-23 17:44 | PRJ-001 | JOB-006 | Elena Voss | Project group | Group Chat | Finish coat Tuesday. No traffic 48 hours. |  | @all | Yes
MSG-008 | 2026-08-24 07:55 | PRJ-001 | TSK-027 | Marcus Webb | Project group | App | Weekly meeting tomorrow 9:00 on site. Agenda in documents. | drive/docs/agenda-0825.pdf | @Alex @Sofia @Maya | No
MSG-009 | 2026-08-24 08:10 | PRJ-001 | AI-005 | Morgan Ellis | Alex Rivera | Email | Contingency dropped below 10%. Recommend pausing water feature. |  | @Alex @Jamie | No
MSG-010 | 2026-08-12 15:02 | PRJ-001 | DOC-009 | Riley Grant | Marcus Webb | App | Electrical rough passed. Final after device install. | drive/insp/elec-rough.pdf | @Marcus | Yes
MSG-011 | 2026-08-18 19:30 | PRJ-002 | RM-09 | Sofia Alvarez | Alex Rivera | App | Cabin Japandi board is in Design Studio. Two fixture directions. | drive/mood/cabin | @Alex | Yes
MSG-012 | 2026-08-19 10:05 | PRJ-001 | SUP-004 | Harper Quinn | Sofia Alvarez | Email | Wolf range crate confirmed for Sep 12 window. |  | @Sofia | Yes

## Inventory
INVENTORY
Everything in the house · insurance + future maintenance
Item ID | Item | Brand | Room / Location | Category | Purchase Date | Cost | Warranty (yrs) | Warranty End | Serial | Model | Receipt | Condition | Replacement Value | Notes
INV-001 | Samsung Refrigerator (existing, to donate) | Samsung | RM-01 | Appliance | 2019-04-01 | 1200 | 1 |  | RF28R7351SG | RF28 | drive/rcpt/old-fridge | Fair | 400 | Pickup scheduled after new fridge arrives
INV-002 | Sub-Zero fridge (on order) | Sub-Zero | RM-01 | Appliance | 2026-09-12 | 0 | 2 |  | TBD | DEC3650 | APPL-01 | On order | 8900 | Serial on delivery
INV-003 | Wolf 36 dual-fuel range (on order) | Wolf | RM-01 | Appliance | 2026-09-12 | 0 | 2 |  | TBD | DF364C | APPL-01 | On order | 7900
INV-004 | Bosch dishwasher | Bosch | RM-01 | Appliance | 2023-06-01 | 980 | 1 |  | FD-2291 | SHPM88Z75N | drive/rcpt/dw | Good | 900 | Reuse
INV-005 | WarmFloor thermostat | WarmFloor | RM-03 | System | 2026-07-06 | 1680 | 3 |  | WF-T-44190 | WF-STAT-2 | WF-441 | New | 1680 | Program 82F mornings
INV-006 | Brizo shower set | Brizo | RM-03 | Fixture | 2026-08-14 | 890 | 5 |  | BZ-100221 | BZ-T600 | FERG-9921 | New | 890
INV-007 | Primary bath vanity | Cascade | RM-03 | Cabinetry | 2026-07-20 | 1680 | 2 |  | CC-VAN-48-09 | CC-VAN-48 | INV-CC-440 | New | 1680
INV-008 | HVAC furnace | Trane | Laundry / mech | HVAC | 2021-09-01 | 4200 | 1 |  | TR-88120 | S9V2 | drive/rcpt/hvac | Good | 3800 | Filter every 90 days
INV-009 | Water heater (heat pump) | Rheem | Laundry / mech | Plumbing | 2024-02-10 | 2100 | 2 |  | RH-44019 | PROPH80 | drive/rcpt/wh | Good | 2000 | Anode 2027
INV-010 | Roof — architectural shingle | Owens Corning | Exterior | Envelope | 2018-07-01 | 9800 | 2 |  |  | Duration | drive/rcpt/roof | Fair | 12000 | Inspect after storms
INV-011 | Washer / dryer pair | LG | RM-07 | Appliance | 2022-11-01 | 1600 | 1 |  | LG-W8821 / LG-D8821 | WM4000 / DLEX4000 | drive/rcpt/ld | Good | 1400
INV-012 | Living room rug (existing) | West Elm | RM-02 | Furniture | 2020-01-15 | 640 | 0 |  |  | Kelim 9x12 |  | Keep | 400 | Clean after flooring
INV-013 | Entry hook rail | Rejuvenation | RM-08 | Hardware | 2026-08-19 | 186 | 1 |  |  | RJ-HR-48 | REJ-33 | New | 186 | Install this week
INV-014 | Smoke / CO detectors x6 | First Alert | Whole home | Safety | 2025-01-08 | 180 | 10 |  |  | SMCO410 |  | Good | 180 | Hush test monthly
INV-015 | Cabin water filter | Berkey | PROP-002 | Plumbing | 2023-05-01 | 320 | 2 |  |  | Royal |  | Good | 280 | Replace elements 2026-11
Formulas:
Warranty End = IF(OR([Item ID]="",[Purchase Date]="",[Warranty (yrs)]=""),"",EDATE([Purchase Date],[Warranty (yrs)]*12))

## Maintenance
MAINTENANCE
The system does not end at handover · HVAC, roof, warranties, pest, water, solar
Maint ID | Item / System | Room / Location | Type | Frequency | Last Service | Next Due | Vendor | Est. Cost | Status | Remind (days) | Notes | Days Until Due | Reminder
MNT-001 | HVAC furnace service | Laundry / mech | HVAC | Annual | 2025-10-12 | 2026-10-12 | Allied Heating | 180 | Upcoming | 14 | Replace filter at service
MNT-002 | Heat-pump water heater flush | Laundry / mech | Plumbing | Annual | 2025-02-10 | 2026-09-10 | Pacific Plumbing | 140 | Due Soon | 14 | Check anode
MNT-003 | Gutter clean + roof walk | Exterior | Envelope | Biannual | 2026-04-02 | 2026-10-15 | Ironwood / roofer | 220 | Upcoming | 14 | After leaf drop
MNT-004 | Paint touch-up interior | Whole home | Finishes | As needed |  | 2026-11-20 | Greenfield Painting | 0 | Upcoming | 7 | Leave labeled quarts
MNT-005 | Pest control | Exterior | Pest | Quarterly | 2026-06-01 | 2026-09-01 | Oregon Pest | 95 | Due Soon | 7
MNT-006 | Radiant floor test | RM-03 | Electrical | Annual | 2026-07-06 | 2027-07-06 | WarmFloor / NWE | 0 | Upcoming | 30 | First winter check
MNT-007 | Appliance warranty photo set | RM-01 | Appliance | Once |  | 2026-09-20 | Alex Rivera | 0 | Upcoming | 3 | After delivery
MNT-008 | Smoke / CO test | Whole home | Safety | Monthly | 2026-08-01 | 2026-09-01 | Alex Rivera | 0 | Upcoming | 3
MNT-009 | Cabin water filter elements | PROP-002 | Plumbing | Annual | 2025-11-01 | 2026-11-01 | Alex Rivera | 60 | Upcoming | 14
MNT-010 | Window weatherstrip | Whole home | Envelope | Annual | 2025-11-15 | 2026-11-10 | Ironwood | 160 | Upcoming | 14 | Before handover winter
MNT-011 | Irrigation blowout | RM-06 | Landscape | Annual | 2025-10-20 | 2026-10-20 | Garden & Gate | 120 | Upcoming | 14 | After path work
MNT-012 | Grout seal — primary bath | RM-03 | Tile | Annual | 2026-08-12 | 2027-08-12 | Heritage Tile | 0 | Complete | 30 | Sealed at install

## Inspections
INSPECTIONS
City + independent · attach reports in the vault
Insp ID | Project ID | Room ID | Type | Inspector | Date | Result | Issues Found | Follow-up | Status | Report Link
INS-001 | PRJ-001 |  | Building permit review | Riley Grant | 2026-04-12 | Pass | None |  | Complete | drive/insp/permit.pdf
INS-002 | PRJ-001 | RM-01 | Electrical rough | Riley Grant | 2026-07-02 | Pass | Add AFCI in pantry — done same day |  | Complete | drive/insp/elec-rough.pdf
INS-003 | PRJ-001 | RM-03 | Plumbing rough | Riley Grant | 2026-06-30 | Pass | None |  | Complete | drive/insp/plumb-rough.pdf
INS-004 | PRJ-001 | RM-03 | Waterproofing / shower pan | Marcus Webb | 2026-07-10 | Pass | None |  | Complete | drive/insp/pan.pdf
INS-005 | PRJ-001 | RM-03 | Primary bath punch | Priya Shah | 2026-08-26 | Scheduled | Haze on niche | Reclean + photo | Scheduled
INS-006 | PRJ-001 |  | Electrical final | Riley Grant | 2026-10-28 | Scheduled |  | After devices | Scheduled
INS-007 | PRJ-001 |  | Plumbing final | Riley Grant | 2026-10-28 | Scheduled |  |  | Scheduled
INS-008 | PRJ-001 |  | Building final | Riley Grant | 2026-11-04 | Scheduled |  | After electrical/plumbing finals | Scheduled
INS-009 | PRJ-001 |  | Independent punch | Alder Inspection Group | 2026-11-08 | Scheduled |  | Pre-handover | Scheduled

## Payments
PAYMENTS
Draws, deposits, scheduled wires · aging for unpaid
Pay ID | Date | Payee Type | Payee | Project ID | Invoice # | Amount | Method | Status | Due Date | Paid Date | Aging (days)
PAY-001 | 2026-03-08 | Designer | Luna Interiors | PRJ-001 | INV-LUNA-110 | 2400 | ACH | Paid | 2026-03-15 | 2026-03-08
PAY-002 | 2026-04-02 | Authority | City of Portland | PRJ-001 | PMT-2026-441 | 840 | Credit Card | Paid | 2026-04-02 | 2026-04-02
PAY-003 | 2026-05-04 | Designer | Luna Interiors | PRJ-001 | INV-LUNA-126 | 1800 | ACH | Paid | 2026-05-18 | 2026-05-04
PAY-004 | 2026-05-22 | Contractor | Ironwood Construction | PRJ-001 | INV-IW-204 | 2800 | Check | Paid | 2026-06-05 | 2026-05-22
PAY-005 | 2026-08-02 | Contractor | Cascade Cabinets | PRJ-001 | INV-CC-501 | 7400 | Wire | Paid | 2026-08-09 | 2026-08-02
PAY-006 | 2026-08-25 | Contractor | Cascade Cabinets | PRJ-001 | INV-CC-502 | 7400 | Wire | Scheduled | 2026-09-08
PAY-007 | 2026-08-28 | Contractor | Cascade Cabinets | PRJ-001 | INV-CC-510 | 3600 | ACH | Scheduled | 2026-09-11
PAY-008 | 2026-08-18 | Contractor | Ironwood Construction | PRJ-001 | INV-IW-228 | 1550 | ACH | Paid | 2026-09-01 | 2026-08-18
PAY-009 | 2026-08-08 | Contractor | Heritage Tile & Stone | PRJ-001 | INV-HT-81 | 2100 | ACH | Paid | 2026-08-22 | 2026-08-08
PAY-010 | 2026-08-01 | Designer | Luna Interiors | PRJ-002 | INV-LUNA-140 | 600 | ACH | Paid | 2026-08-15 | 2026-08-01
PAY-011 | 2026-09-12 | Supplier | Article | PRJ-001 | ART-SOFA | 3400 | Credit Card | Draft | 2026-09-12

## Change Orders
CHANGE ORDERS
Scope, cost, and schedule impacts · negative cost = savings
CO ID | Project ID | Room ID | Description | Requested By | Date | Cost Impact | Schedule Impact (days) | Status | Approved By
CO-001 | PRJ-001 | RM-03 | Swap marble floor for porcelain HT-8841 | Sofia Alvarez / AI | 2026-05-18 | -1640 | 0 | Implemented | Alex Rivera
CO-002 | PRJ-001 | RM-01 | Island surface: porcelain slab instead of marble | Sofia Alvarez / AI | 2026-08-21 | -460 | 2 | Submitted
CO-003 | PRJ-001 | RM-01 | Add pot-filler at range | Alex Rivera | 2026-06-10 | 480 | 1 | Approved | Alex Rivera
CO-004 | PRJ-001 | RM-02 | Site-cut oak nosing in lieu of factory (backorder) | Elena Voss | 2026-08-21 | 0 | 0 | Approved | Marcus Webb
CO-005 | PRJ-001 | RM-06 | Hold water feature until contingency recovers | Morgan Ellis / AI | 2026-08-24 | -1800 | 0 | Draft

## Permits
PERMITS
Authority, fees, expiration reminders
Permit ID | Project ID | Type | Authority | Applied | Approved | Number | Fee | Expiration | Status | Document Link | Days to Expiry
PMT-001 | PRJ-001 | Building — residential remodel | City of Portland | 2026-04-02 | 2026-04-12 | 2026-REM-44182 | 840 | 2027-04-12 | Approved | drive/docs/permit-441.pdf
PMT-002 | PRJ-001 | Electrical | City of Portland | 2026-04-18 | 2026-04-22 | 2026-EL-11904 | 310 | 2027-04-22 | Approved | drive/docs/permit-el.pdf
PMT-003 | PRJ-001 | Plumbing | City of Portland | 2026-04-18 | 2026-04-22 | 2026-PL-7731 | 300 | 2027-04-22 | Approved | drive/docs/permit-pl.pdf
PMT-004 | PRJ-001 | Right-of-way dumpster | PBOT | 2026-05-10 | 2026-05-14 | ROW-5521 | 75 | 2026-06-14 | Closed | drive/docs/row.pdf
PMT-005 | PRJ-002 | Building — bath remodel | Hood River County |  |  |  | 0 |  | Not Started

## Warranties
WARRANTIES
Labor and product coverage after handover
Warranty ID | Project ID | Item / Work | Provider | Start | End | Term (months) | Coverage | Claim Process | Doc Link | Days Remaining
WAR-001 | PRJ-001 | Heritage tile labor + material | Heritage Tile & Stone | 2026-08-12 | 2028-08-12 | 24 | Labor + setting materials | Photo + email Priya | drive/warr/heritage.pdf
WAR-002 | PRJ-001 | WarmFloor system | WarmFloor Co. | 2026-07-06 | 2029-07-06 | 36 | Mat + thermostat | Serial + install photos | drive/warr/wf.pdf
WAR-003 | PRJ-001 | White oak flooring finish | Timberline Floors | 2026-08-28 | 2027-08-28 | 12 | Site finish wear | No steam mops year 1
WAR-004 | PRJ-001 | Cascade cabinetry | Cascade Cabinets | 2026-09-15 | 2028-09-15 | 24 | Boxes, doors, finish | Maya Chen
WAR-005 | PRJ-001 | Wolf range (pending delivery) | Sub-Zero Group | 2026-09-12 | 2028-09-12 | 24 | Parts + labor | Register online 30 days
WAR-006 | PRJ-001 | Sub-Zero fridge (pending) | Sub-Zero Group | 2026-09-12 | 2028-09-12 | 24 | Sealed system 5yr | Register online 30 days
WAR-007 | PRJ-001 | Brizo fixtures | Brizo / Ferguson | 2026-08-14 | 2031-08-14 | 60 | Finish + function | Proof of purchase | FERG-9921

## Calendar
CALENDAR
Visits, deliveries, inspections, reminders · also subscribe via the Apps Script
Date | Time | Event | Project / Property | Detail | Owner | Status
2026-08-25 | 09:00 | Site meeting | PRJ-001 | Weekly GC / designer / homeowner | Marcus Webb | Scheduled
2026-08-25 | 07:30 | Cabinet install | PRJ-001 | Cascade — box set continues | Maya Chen | Scheduled
2026-08-26 | 10:00 | Bath punch | PRJ-001 | Heritage reclean + walk | Priya Shah | Scheduled
2026-08-27 | All day | Hardware ETA | PRJ-001 | Pulls expected — do not hang if late | Maya Chen | Watch
2026-08-28 | All day | Floor finish cure | PRJ-001 | No traffic 48 hours after Tuesday coat | Elena Voss | Scheduled
2026-09-01 | 17:00 | Order sofa | PRJ-001 | 6-week lead — last day to hit Oct move-in | Sofia Alvarez | To Do
2026-09-01 | All day | Pest control due | PROP-001 | Oregon Pest quarterly | Alex Rivera | Due Soon
2026-09-04 | 08:00 | Counter template | PRJ-001 | After doors hung | Heritage Tile | Scheduled
2026-09-10 | 07:00 | Painting starts | PRJ-001 | Guest, dining, entry | Leo Park | Scheduled
2026-09-10 | All day | Water heater flush due | PROP-001 | Pacific Plumbing | Sam Ortiz | Due Soon
2026-09-12 | Window | Appliance delivery | PRJ-001 | Wolf + Sub-Zero | Aiden Brooks | Scheduled
2026-10-06 | 07:00 | Exterior path start | PRJ-001 | Release only if contingency healthy | Theo Brooks | Hold
2026-10-12 | All day | HVAC annual service | PROP-001 | Allied Heating | Alex Rivera | Upcoming
2026-11-04 | 09:00 | Building final | PRJ-001 | City of Portland | Riley Grant | Scheduled
2026-11-10 | 10:00 | Handover walkthrough | PRJ-001 | Punch + vault packet | Marcus Webb | To Do

## Notifications
NOTIFICATIONS
In-app / email / SMS queue · mark Status = Read when handled
ID | Date | Severity | Module | Message | Status | Audience
NTF-001 | 2026-08-24 | Warning | Budget | Kitchen budget is 12% over original target. Island swap pending. | Open | HO-001
NTF-002 | 2026-08-24 | Critical | Finance | Project contingency has fallen below 10%. | Open | HO-001
NTF-003 | 2026-08-24 | Success | Rooms | Primary bathroom is under budget after porcelain swap. | Open | HO-001
NTF-004 | 2026-08-23 | Warning | Procurement | White oak stair nosing backordered 11 days. | Open | PM-001
NTF-005 | 2026-08-22 | Info | Schedule | Cabinet hardware still in transit — hardware day next week. | Open | CT-001
NTF-006 | 2026-08-20 | Info | Visit | Cascade Cabinets on site Aug 25–27 for box set. | Open | HO-001
NTF-007 | 2026-08-18 | Warning | Approval | CO-002 island porcelain awaiting signature. | Open | HO-001
NTF-008 | 2026-09-01 | Info | Maintenance | Pest control due in 8 days. | Scheduled | HO-001
NTF-009 | 2026-08-24 | Info | Message | Marcus posted tomorrow's site meeting agenda. | Open | HO-001
NTF-010 | 2026-08-12 | Success | Inspection | Electrical rough passed. | Read | PM-001

## Users
USERS
Nine roles · each role sees a different dashboard in the product
User ID | Name | Email | Phone | Role | Company | Status | Last Login | Permissions
HO-001 | Alex Rivera | alex.rivera@email.example | +1-503-555-0148 | Homeowner | Rivera Household | Active | 2026-08-24 | Full project visibility, approvals, payments
AD-001 | Morgan Ellis | morgan@hearthandtimber.example | +1-503-555-0100 | Admin | Hearth & Timber | Active | 2026-08-24 | System admin, all properties
PM-001 | Marcus Webb | marcus@ironwood.build | +1-503-555-0172 | Project Manager | Ironwood Construction | Active | 2026-08-23 | Schedule, contractors, inspections
DS-001 | Sofia Alvarez | sofia@lunainteriors.example | +1-503-555-0194 | Interior Designer | Luna Interiors | Active | 2026-08-22 | Design studio, materials, mood boards
CT-001 | Maya Chen | maya@cascadecabinets.example | +1-503-555-0111 | Contractor | Cascade Cabinets | Active | 2026-08-21 | Kitchen millwork
SC-001 | Devon Ruiz | devon@nw-electric.example | +1-503-555-0133 | Subcontractor | Northwest Electric | Active | 2026-08-20 | Electrical rough and finish
SU-001 | Harper Quinn | orders@tileandtimber.example | +1-503-555-0160 | Supplier | Tile & Timber Co. | Active | 2026-08-18 | Materials, lead times
IN-001 | Riley Grant | r.grant@portland.gov.example | +1-503-555-0188 | Inspector | City of Portland | Active | 2026-08-12 | Building, electrical, plumbing
AC-001 | Jamie Cole | jamie@hearthandtimber.example | +1-503-555-0108 | Accountant | Hearth & Timber | Active | 2026-08-24 | Invoices, tax, payments

## Properties
PROPERTIES
Multi-property digital twin · one row per home
Property ID | Name | Street | City | State | Postal | Country | Type | Year Built | Sq Ft | Stories | Beds | Baths | Owner | Owner User ID | Insurance Policy | Insurance Year | Notes
PROP-001 | Maplewood Residence | 1847 Maplewood Drive | Portland | OR | 97214 | USA | Single Family | 1928 | 2480 | 2 | 4 | 2.5 | Alex Rivera | HO-001 | State Farm HO-34821 | 2027 | Craftsman with later additions. Knob-and-tube mostly retired.
PROP-002 | Columbia Gorge Cabin | 88 Ridge Trail | Hood River | OR | 97031 | USA | Cabin | 1998 | 980 | 1 | 2 | 1 | Alex Rivera | HO-001 | State Farm HO-34822 | 2027 | Weekend cabin. Bath refresh only.

## Roles & Permissions
ROLES & PERMISSIONS
Who can see and change what · enforce in the live product; this matrix is the source of truth
Module \ Role | Homeowner | Admin | Project Manager | Interior Designer | Contractor | Subcontractor | Supplier | Inspector | Accountant
Dashboard | F | F | F | V | V | V | — | V | V
Projects | F | F | F | V | V | V | — | V | V
Rooms | F | F | F | F | V | V | — | V | —
Design Studio | F | F | V | F | V | — | — | — | —
AI Insights | V | F | V | F | — | — | — | — | —
Budget | V | F | F | V | — | — | — | — | F
Expenses | E | F | F | V | E | — | — | — | F
Finance | V | F | F | V | — | — | — | — | F
Contractors | V | F | F | V | V | — | — | V | V
Quotes | V | F | F | V | V | — | V | — | V
Jobs | V | F | F | V | F | F | — | V | V
Tasks | E | F | F | F | F | F | — | V | —
Materials | V | F | F | F | E | E | F | — | V
Documents | bar: V E V to V — V
Messages | F | F | F | F | F | F | E | V | —
Inventory | F | F | V | V | — | — | — | — | —
Maintenance | F | F | F | V | V | — | — | — | —
Inspections | V | F | F | — | V | V | — | F | —
Payments | V | F | F | — | V | — | V | — | F
Change Orders | A | F | A | V | V | — | — | — | V
Permits | V | F | F | — | V | — | — | F | V
Admin | — | F | V | — | — | — | — | — | V
Settings | — | F | V | — | — | — | — | — | —
Users | — | F | V | — | — | — | — | — | V
F = full · E = edit own records · V = view · A = approve · — = no access

## Admin
ADMIN
System administrator · portfolio of all homeowners and projects
HOMEOWNERS |  |  | ACTIVE PROJECTS |  |  | COMPLETED |  | CONTRACTORS
Active household accounts |  |  | In construction or design |  |  | Renovations handed over |  | In the bench
PORTFOLIO VALUE |  |  | REVENUE (PAID) |  |  | DELAYED TASKS |  | OPEN DISPUTES
Sum of project budgets |  |  | Cash out recorded |  |  | Across all projects |  | Jobs + payments
PENDING APPROVALS |  |  | OPEN MESSAGES |  |  | PERMITS OPEN |  | MAINT DUE
COs + quotes |  |  | Unread |  |  | Not closed |  | Aftercare load
PROJECT PORTFOLIO
Project | Property | Status | Phase | Budget | Spent | Health | Progress
PRJ-001
PRJ-002
SUPPLIER PERFORMANCE (lead time vs rating)
Supplier | Category | Rating | Lead days

## Settings
SETTINGS
Company, currency, thresholds · change values in column B
Setting | Value | Notes
Company Name | Hearth & Timber
Product Name | Home Renovation Management System
Version | 1.0.0
Homeowner | Alex Rivera
Active Project ID | PRJ-001 | Default filter for dashboard KPIs.
Active Property ID | PROP-001
Currency | USD | USD formulas use $ format; change display only.
Currency Symbol | $
Language | English
Contingency % | 10% | Used by Finance + alerts. Default 10%.
Fiscal Year Start | 2026-01-01
Today (system) | 2026-08-24 | Dashboard 'today'. Update if you archive this file later.
Timezone | America/Los_Angeles
Tax Rate | 0% | Optional. Applied on Finance tax line if > 0.
Default Payment Terms (days) | 14
Maintenance Reminder (days) | 14
Document Expiry Reminder (days) | 30
Low Contingency Threshold | 10% | Alert when remaining contingency / budget < this.
Budget Overrun Alert % | 10% | Room/category alert when spent+committed exceeds planned by this.
Support Email | studio@hearthandtimber.example
Primary Color | #16352F
Secondary Color | #E8DDCB
Accent Color | #C86B4A
Background Color | #F8F6F1
Success Color | #719B7A
Warning Color | #D99A3D
Danger Color | #C75C5C

## Lookups
LOOKUPS
Dropdown sources · do not delete · add values downward
These lists power every dropdown in the workbook. Add new items in the first empty cell of a column.
Project Status | Project Phase | Room Type | Room Status | Design Style | Design Item | Budget Category | Expense Status | Payment Method | Trade | Task Status | Priority | Material Status | Doc Category | Role | Quote Status | Job Status | Insp Result | Payment Status | CO Status | Permit Status | Maint Status | Insight Severity | Insight Status | Channel | Currency | Language | Property Type
Planning | Planning | Kitchen | Not Started | Modern | Mood Board | Labor | Planned | ACH | General Contractor | To Do | Critical | Required | Contract | Homeowner | Requested | Assigned | Pass | Draft | Draft | Not Started | Upcoming | Info | New | App | USD | English | Single Family
Active | Design | Living Room | Design | Minimal | Color Palette | Materials | Committed | Check | Interior Designer | Scheduled | High | Quoted | Invoice | Admin | Received | Scheduled | Conditional | Scheduled | Submitted | Applied | Due Soon | Opportunity | Accepted | Email | EUR | Spanish | Townhouse
On Hold | Permits | Bedroom | In Progress | Scandinavian | Material Board | Design | Paid | Credit Card | Architect | In Progress | Medium | Approved | Receipt | Project Manager | Compared | In Progress | Fail | Paid | Approved | In Review | Overdue | Warning | In Progress | SMS | GBP | French | Condo
Completed | Demolition | Primary Bedroom | Punch List | Luxury | Furniture | Permits | Void | Wire | Cabinetry | Inspection | Low | Ordered | Floor Plan | Interior Designer | Accepted | Milestone Review | Scheduled | Overdue | Rejected | Approved | Scheduled | Critical | Dismissed | Group Chat | CAD | German | Multi-Family
Cancelled | Rough-In | Bathroom | Complete | Industrial | Flooring | Delivery |  | Cash | Electrical | Completed |  | Shipped | Building Permit | Contractor | Rejected | Complete |  | Disputed | Implemented | Expired | Complete |  | Resolved | Task Comment | AUD | Portuguese | Cabin
| Construction | Primary Bathroom |  | Traditional | Wall | Contingency |  | Financing | Plumbing | Blocked |  | Delivered | License | Subcontractor | Expired | Disputed |  |  |  | Closed |  |  |  | Photo Comment | INR | Arabic | Commercial
| Finishes | Powder Room |  | Transitional | Ceiling | Appliances |  |  | Tile & Stone |  |  | Installed | Insurance | Supplier | [9 empty] | Voice | AED | Hindi
| Furnishing | Dining Room |  | Japandi | Lighting | Furniture |  |  | Painting |  |  | Returned | Warranty | Inspector
| Inspection | Office |  | Mediterranean | Cabinetry | Inspections |  |  | Flooring |  |  | Backordered | Inspection Report | Accountant
| Handover | Garage |  | Coastal | Hardware | Other |  |  | Lighting |  |  |  | Product Manual
| Maintenance | Exterior |  |  | 2D Floor Plan |  |  |  | HVAC |  |  |  | Photo
|  | Garden |  |  | 3D Visualization |  |  |  | Carpentry |  |  |  | Agreement
|  | Laundry |  |  | AI Concept |  |  |  | Roofing |  |  |  | Change Order
|  | Entry / Foyer | [6 empty] | Landscaping |  |  |  | Quote
|  | Hallway | [6 empty] | Windows & Doors
|  | Basement | [6 empty] | Appliance
|  | Attic | [6 empty] | Inspection
Custom

## Audit Log
AUDIT LOG
Who changed what · append-only in the live product
Audit ID | Timestamp | User ID | User Name | Module | Record ID | Action
AUD-001 | 2026-08-24 08:10 | AD-001 | Morgan Ellis | AI Insights | AI-005 | Created contingency alert
AUD-002 | 2026-08-21 16:22 | HO-001 | Alex Rivera | Change Orders | CO-002 | Approved design direction (pending formal sign)
AUD-003 | 2026-08-21 14:05 | DS-001 | Sofia Alvarez | Design Studio | DSN-006 | Published porcelain material board
AUD-004 | 2026-08-20 07:40 | CT-001 | Maya Chen | Materials | MAT-001 | Marked cabinets Delivered
AUD-005 | 2026-08-18 17:02 | AC-001 | Jamie Cole | Payments | PAY-008 | Recorded Ironwood August draw
AUD-006 | 2026-08-14 11:00 | PM-001 | Marcus Webb | Inspections | INS-002 | Attached electrical rough report
AUD-007 | 2026-08-12 15:02 | IN-001 | Riley Grant | Inspections | INS-002 | Result = Pass
AUD-008 | 2026-08-02 09:15 | HO-001 | Alex Rivera | Payments | PAY-005 | Wired Cascade deposit
AUD-009 | 2026-05-18 10:00 | DS-001 | Sofia Alvarez | Change Orders | CO-001 | Implemented marble→porcelain
AUD-010 | 2026-03-04 16:45 | HO-001 | Alex Rivera | Documents | DOC-001 | Signed GC agreement